## Ark1
Discipline | Task | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | Total
| Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
All Discipline | Kickoff with customer | 3 | [22 empty] | 3
Design | Gather inspo for customer | 4 | 7.5 | 7.5 | [20 empty] | 19
Design / Coding | Deliever suggestion |  |  |  | 2 | 7.5 | [18 empty] | 9.5
Customer | Accept/Comment on layout |  |  |  |  | 7.5 | [18 empty] | 7.5
Design / Customer | Design Freeze | [7 empty] | 1 | [15 empty] | 1
Photographer | Photos for website |  | 7.5 | [21 empty] | 7.5
Design | Design | [7 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  |  |  | 7.5 | 7.5 | [6 empty] | 52.5
Coding | Coding | [7 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  |  |  | 7.5 | 7.5 | [6 empty] | 52.5
Design | Presentation | [14 empty] | 4 | [8 empty] | 4
Customer | Final Comments | [14 empty] | 3 | [8 empty] | 3
Coding | Testing | [17 empty] | 7.5 | 7.5 |  |  |  |  | 15
All Discipline | Report | [16 empty] | 7.5 |  |  |  |  | 7.5 |  | 15
All Discipline | Deliever final product | [22 empty] | 1 | 1
| Total man hours | 7 | 15 | 7.5 | 2 | 15 | 0 | 0 | 16 | 15 | 15 | 15 | 15 | 0 | 0 | 7 | 15 | 22.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 0 | 189.5
Main assignment
No work done (weekend)
Independent work
Assignment must be done within this time
Customer hours